## Roster & Legend
PROJECT ROSTER — Efficient, Shortcut-Resistant & Explainable CNN for Chest X-ray (5-member team)
Every member trains/fits at least one model (ML task) AND owns a framework stage AND paper sections. No pretrained models — all trained from scratch.
Code | Member / Role | Hands-on ML task (trains/fits a model) | Framework stage owned | Paper Sections | Key Deliverables
M1 | Member 1 — Baseline CNN & Reproducibility/Lit Lead | Trains & tunes the from-scratch baseline CNN | Baseline model + repo/tracking/seeds | Introduction, Related Work, Abstract | Baseline model + tuning; reproducible repo; literature
M2 | Member 2 — Data + Lung-Seg & Recipe-Model Lead | Trains a lung-segmentation U-Net + the shortcut-recipe model | Data pipeline + preprocessing + recipe | Dataset, Experimental Setup | U-Net; pipeline; recipe-trained model
M3 | Member 3 — LiteCXR-Net Architecture Lead | Designs & trains LiteCXR-Net (+ HP tuning) | Proposed architecture + tuning | Proposed Framework | LiteCXR-Net; comparison; slides
M4 | Member 4 — Ablation-Model & Efficiency Lead | Trains & evaluates all ablation model variants | Ablations + efficiency benchmark | Experiments (efficiency, ablation) | Ablation models; efficiency; figures
M5 | Member 5 — Robustness, Calibration & Explainability Lead | Trains no-recipe control model + fits temperature-scaling calibration | Robustness + calibration + XAI + assembly | Results, Discussion, Conclusion | Control model; OOD tests; calibration; XAI; paper
LEGEND
[ML] tasks | Tasks marked [ML] in the Master Task List involve training or fitting a model. Every member owns at least one.
Status values | Not started / In progress / Blocked / Done (dropdown in Master Task List, column J)
Milestone codes | M0 End W1 · M1 End W2 · M2 Mid W3 · M3 End W3 · M4 End W4 (see 'Milestones & Gates' tab)
[GATE] | A checkpoint that blocks downstream work until signed off.
Owner | Person accountable (does the work). Support = assists / reviews (RACI).
Rule §11 | Each member contributes to an identifiable DNN stage — a hands-on ML task, not just writing.

## Milestones & Gates
MAIN MILESTONES & GATES
Milestone | Due | Name | Gate criteria (must all be true to pass) | Sign-off owner
M0 | End of Week 1 | Baseline & Pipeline Ready | Data pipeline + lung-mask (U-Net) ready; from-scratch baseline CNN trains end-to-end; baseline HP tuning started. Feeds the ACM proposal. | M2 / M1
M1 | End of Week 2 | Proposed Model Trained | Baseline fully evaluated (with HP tuning); LiteCXR-Net v1 trained; recipe-trained variant started; comparison complete. | M1 / M3
M2 | Mid Week 3 | Efficiency & Ablations Done | Computational analysis + all trained ablation variants + proposed-model HP tuning complete. | M4 / M3
M3 | End of Week 3 | Robustness, XAI & Calibration Done | Control model trained; external/OOD robustness + Grad-CAM faithfulness + temperature-scaling calibration complete. | M5
M4 | End of Week 4 | Paper & Slides Ready | Consolidated results, Pareto trade-off, full paper draft, slides; reproducibility rerun passes. | M1 / M5

## Master Task List
MASTER TASK LIST — single source of truth (update Status in column J). [ML] = trains/fits a model
ID | Epic | Task / Sub-issue | Owner | Support | Week | M.stone | Depends on | Est. days | Status | Notes
T01 | 0 Setup | Create GitHub repo, branch strategy & folder layout (data/ src/ notebooks/ results/ paper/) | M1 | All | W1 | M0 | - | 1 | Not started
T02 | 0 Setup | Set up experiment tracking (W&B/TensorBoard) + fixed-seed reproducibility standard | M1 | M5 | W1 | M0 | T01 | 1 | Not started
T03 | 0 Setup | Compute setup: Colab/Kaggle GPU, requirements.txt, mixed-precision config | M4 | M2 | W1 | M0 | T01 | 1 | Not started
T04 | 0 Setup | Define shared config: image size (224 + 128 fast-mode), split ratios, metrics schema, checkpoint format | M5 | All | W1 | M0 | T01 | 1 | Not started
T05 | 1 Data | Download COVID-19 Radiography dataset; integrity check; class-count EDA | M2 | M1 | W1 | M0 | - | 1 | Not started
T06 | 1 Data | Preprocessing module (resize, grayscale->3ch, normalise) | M2 | M3 | W1 | M0 | T04 | 1 | Not started
T07 | 1 Data | [ML] Train a lightweight lung-segmentation U-Net to generate lung masks | M2 | M5 | W1-W2 | M0 | T06 | 2 | Not started
T08 | 1 Data | Augmentation module (rotation, flip, jitter, CLAHE, random erasing) | M2 | M4 | W1 | M0 | T06 | 1 | Not started
T09 | 1 Data | Stratified 70/15/15 split (fixed seed) + saved index files | M2 | M5 | W1 | M0 | T06 | 1 | Not started
T10 | 1 Data | Shared PyTorch DataLoader with class weights for imbalance | M2 | M1 | W1 | M0 | T08,T09 | 1 | Not started
T11 | 1 Data | Prepare external / source-stratified robustness set (test only) | M5 | M2 | W1-W2 | M1 | T06 | 2 | Not started
T12 | 2 Baseline | Implement from-scratch baseline CNN (ResNet-18-style, NO pretrained weights) | M1 | M3 | W1 | M0 | T10 | 2 | Not started
T13 | 2 Baseline | Shared training-loop template (from scratch) | M5 | M1 | W1 | M0 | T10 | 1 | Not started
T14 | 2 Baseline | [ML] Train baseline CNN end-to-end to validate pipeline [GATE M0] | M1 | All | W1 | M0 | T12,T13 | 1 | Not started
T15 | 2 Baseline | [ML] Baseline hyper-parameter tuning (LR, batch, weight decay, aug strength) | M1 | - | W2 | M1 | T14 | 2 | Not started
T16 | 2 Baseline | Baseline full evaluation (accuracy, F1, AUROC, confusion matrix) | M1 | - | W2 | M1 | T15 | 1 | Not started
T17 | 3 LiteCXR | Design LiteCXR-Net (depthwise-separable blocks + compact head) | M3 | M1 | W2 | M1 | T10 | 2 | Not started
T18 | 3 LiteCXR | Add width-multiplier alpha control (0.5 / 0.75 / 1.0) | M3 | - | W2 | M1 | T17 | 1 | Not started
T19 | 3 LiteCXR | Add lightweight channel-attention (SE-style) block | M3 | - | W2 | M1 | T17 | 1 | Not started
T20 | 3 LiteCXR | [ML] Train LiteCXR-Net v1 from scratch | M3 | M5 | W2 | M1 | T18,T19,T13 | 2 | Not started
T21 | 3 LiteCXR | Baseline vs LiteCXR-Net comparison (accuracy / F1 / AUROC) | M3 | M4 | W2 | M1 | T20,T16 | 1 | Not started
T22 | 4 Recipe | [ML] Train LiteCXR-Net WITH the lung-focused shortcut-mitigation recipe | M2 | M3 | W2 | M1 | T07,T20 | 2 | Not started
T23 | 4 Recipe | Tune augmentation / recipe strength for robustness | M2 | M5 | W3 | M2 | T22 | 1 | Not started
T24 | 4 Recipe | [ML] (Optional) add & train lightweight debiasing regulariser | M2 | - | W3 | M2 | T22 | 1 | Not started
T25 | 5 HP-Tune | [ML] LiteCXR-Net hyper-parameter tuning (alpha, LR, batch, weight decay) | M3 | M4 | W3 | M2 | T20 | 2 | Not started
T26 | 6 Ablation | [ML] Train & evaluate ablation: depthwise-separable vs standard convolution | M4 | M3 | W3 | M2 | T20 | 1 | Not started
T27 | 6 Ablation | [ML] Train & evaluate ablation: with / without attention block | M4 | M3 | W3 | M2 | T20 | 1 | Not started
T28 | 6 Ablation | [ML] Train & evaluate ablation: with / without lung-focus recipe | M4 | M2 | W3 | M2 | T22 | 1 | Not started
T29 | 6 Ablation | [ML] Train & evaluate ablation: width-multiplier alpha sweep (0.5/0.75/1.0) | M4 | M3 | W3 | M2 | T18 | 1 | Not started
T30 | 7 Efficiency | Efficiency harness (params, FLOPs, latency CPU/GPU, memory, training time) [GATE M2] | M4 | M5 | W3 | M2 | T20 | 1 | Not started
T31 | 7 Efficiency | Run computational analysis on baseline + LiteCXR-Net + alpha variants | M4 | M5 | W3 | M2 | T30,T16 | 1 | Not started
T32 | 7 Efficiency | Accuracy-efficiency trade-off (Pareto) curve | M4 | M3 | W3-W4 | M2 | T31 | 1 | Not started
T33 | 8 Robust | External-test protocol (label mapping, OOD metrics) | M5 | M1 | W3 | M3 | T11 | 1 | Not started
T34 | 8 Robust | Baseline robustness test (internal vs external drop) | M5 | - | W3 | M3 | T33,T16 | 1 | Not started
T35 | 8 Robust | [ML] Train LiteCXR-Net control (NO recipe) for the robustness comparison | M5 | M3 | W3 | M3 | T20 | 1 | Not started
T36 | 8 Robust | LiteCXR-Net robustness test: recipe vs control (internal vs external drop) | M5 | M2 | W3 | M3 | T33,T22,T35 | 1 | Not started
T37 | 9 XAI | Grad-CAM module (last convolutional layer) [GATE M3] | M5 | M3 | W3 | M3 | T20 | 1 | Not started
T38 | 9 XAI | Lung-localisation faithfulness score (mask-overlap metric) | M5 | M2 | W3 | M3 | T37,T07 | 1 | Not started
T39 | 9 XAI | Faithfulness + heatmaps: baseline vs LiteCXR-Net | M5 | - | W3 | M3 | T38,T16 | 1 | Not started
T40 | 10 Calib | [ML] Fit temperature-scaling calibration (learned scalar) + reliability, baseline vs proposed | M5 | M4 | W3-W4 | M3 | T16,T20 | 1 | Not started
T41 | 11 Analysis | Consolidate all metrics into master results tables | M5 | M1 | W4 | M4 | T31,T36,T39 | 1 | Not started
T42 | 11 Analysis | Statistical comparison (significance, confidence intervals) | M5 | M4 | W4 | M4 | T41 | 1 | Not started
T43 | 11 Analysis | Generate all figures (curves, Pareto, heatmaps, reliability) | M4 | M3 | W4 | M4 | T41 | 1 | Not started
T44 | 12 Paper | Introduction + Related Work | M1 | M5 | W1-W4 | M4 | - | 3 | Not started
T45 | 12 Paper | Dataset + Experimental Setup | M2 | M1 | W2-W4 | M4 | - | 2 | Not started
T46 | 12 Paper | Proposed Framework (LiteCXR-Net) section | M3 | M5 | W2-W4 | M4 | - | 2 | Not started
T47 | 12 Paper | Experiments (efficiency + ablation) section | M4 | All | W4 | M4 | T41 | 2 | Not started
T48 | 12 Paper | Results + Discussion + Conclusion | M5 | All | W4 | M4 | T41 | 2 | Not started
T49 | 12 Paper | Abstract | M1 | M5 | W4 | M4 | T48 | 1 | Not started
T50 | 12 Paper | Presentation slides | M3 | All | W4 | M4 | T41 | 2 | Not started
T51 | 12 Paper | Reference management (Zotero) — ongoing | M1 | All | W1-W4 | M4 | - | 1 | Not started
T52 | 12 Paper | Final proofread + reproducibility rerun from clean repo [GATE M4] | M5 | All | W4 | M4 | T47,T48 | 1 | Not started

## M1 Board
Member 1 — Baseline CNN & Reproducibility/Lit Lead
YOUR HANDS-ON ML TASK: Trains & tunes the from-scratch baseline CNN (T14, T15)
TASKS YOU OWN (accountable)
ID | Epic | Task / Sub-issue | Week | M.stone | Depends on | Est. days | Deliverable
T01 | 0 Setup | Create GitHub repo, branch strategy & folder layout (data/ src/ notebooks/ results/ paper/) | W1 | M0 | - | 1 | Repo + README + branch rules
T02 | 0 Setup | Set up experiment tracking (W&B/TensorBoard) + fixed-seed reproducibility standard | W1 | M0 | T01 | 1 | Tracking project + seed policy
T12 | 2 Baseline | Implement from-scratch baseline CNN (ResNet-18-style, NO pretrained weights) | W1 | M0 | T10 | 2 | baseline_cnn.py
T14 | 2 Baseline | [ML] Train baseline CNN end-to-end to validate pipeline [GATE M0] | W1 | M0 | T12,T13 | 1 | Baseline checkpoint + confusion matrix
T15 | 2 Baseline | [ML] Baseline hyper-parameter tuning (LR, batch, weight decay, aug strength) | W2 | M1 | T14 | 2 | Baseline tuning results
T16 | 2 Baseline | Baseline full evaluation (accuracy, F1, AUROC, confusion matrix) | W2 | M1 | T15 | 1 | Baseline metrics
T44 | 12 Paper | Introduction + Related Work | W1-W4 | M4 | - | 3 | Paper sect. 1-2
T49 | 12 Paper | Abstract | W4 | M4 | T48 | 1 | Abstract
T51 | 12 Paper | Reference management (Zotero) — ongoing | W1-W4 | M4 | - | 1 | Bibliography
ALSO SUPPORTING (assist / review)
ID | Task / Sub-issue | Owner | Week
T04 | Define shared config: image size (224 + 128 fast-mode), split ratios, metrics schema, checkpoint format | M5 | W1
T05 | Download COVID-19 Radiography dataset; integrity check; class-count EDA | M2 | W1
T10 | Shared PyTorch DataLoader with class weights for imbalance | M2 | W1
T13 | Shared training-loop template (from scratch) | M5 | W1
T17 | Design LiteCXR-Net (depthwise-separable blocks + compact head) | M3 | W2
T33 | External-test protocol (label mapping, OOD metrics) | M5 | W3
T41 | Consolidate all metrics into master results tables | M5 | W4
T45 | Dataset + Experimental Setup | M2 | W2-W4
T47 | Experiments (efficiency + ablation) section | M4 | W4
T48 | Results + Discussion + Conclusion | M5 | W4
T50 | Presentation slides | M3 | W4
T52 | Final proofread + reproducibility rerun from clean repo [GATE M4] | M5 | W4

## M2 Board
Member 2 — Data + Lung-Segmentation & Recipe-Model Lead
YOUR HANDS-ON ML TASK: Trains the lung-segmentation U-Net and the shortcut-recipe model (T07, T22)
TASKS YOU OWN (accountable)
ID | Epic | Task / Sub-issue | Week | M.stone | Depends on | Est. days | Deliverable
T05 | 1 Data | Download COVID-19 Radiography dataset; integrity check; class-count EDA | W1 | M0 | - | 1 | Verified dataset + EDA notes
T06 | 1 Data | Preprocessing module (resize, grayscale->3ch, normalise) | W1 | M0 | T04 | 1 | preprocess.py
T07 | 1 Data | [ML] Train a lightweight lung-segmentation U-Net to generate lung masks | W1-W2 | M0 | T06 | 2 | Trained U-Net + lung masks
T08 | 1 Data | Augmentation module (rotation, flip, jitter, CLAHE, random erasing) | W1 | M0 | T06 | 1 | augment.py
T09 | 1 Data | Stratified 70/15/15 split (fixed seed) + saved index files | W1 | M0 | T06 | 1 | split index files
T10 | 1 Data | Shared PyTorch DataLoader with class weights for imbalance | W1 | M0 | T08,T09 | 1 | dataloader.py (shared)
T22 | 4 Recipe | [ML] Train LiteCXR-Net WITH the lung-focused shortcut-mitigation recipe | W2 | M1 | T07,T20 | 2 | Recipe-trained model
T23 | 4 Recipe | Tune augmentation / recipe strength for robustness | W3 | M2 | T22 | 1 | Tuned recipe
T24 | 4 Recipe | [ML] (Optional) add & train lightweight debiasing regulariser | W3 | M2 | T22 | 1 | Optional regularised model
T45 | 12 Paper | Dataset + Experimental Setup | W2-W4 | M4 | - | 2 | Paper sect. (setup)
ALSO SUPPORTING (assist / review)
ID | Task / Sub-issue | Owner | Week
T01 | Create GitHub repo, branch strategy & folder layout (data/ src/ notebooks/ results/ paper/) | M1 | W1
T03 | Compute setup: Colab/Kaggle GPU, requirements.txt, mixed-precision config | M4 | W1
T04 | Define shared config: image size (224 + 128 fast-mode), split ratios, metrics schema, checkpoint format | M5 | W1
T11 | Prepare external / source-stratified robustness set (test only) | M5 | W1-W2
T14 | [ML] Train baseline CNN end-to-end to validate pipeline [GATE M0] | M1 | W1
T28 | [ML] Train & evaluate ablation: with / without lung-focus recipe | M4 | W3
T36 | LiteCXR-Net robustness test: recipe vs control (internal vs external drop) | M5 | W3
T38 | Lung-localisation faithfulness score (mask-overlap metric) | M5 | W3
T47 | Experiments (efficiency + ablation) section | M4 | W4
T48 | Results + Discussion + Conclusion | M5 | W4
T50 | Presentation slides | M3 | W4
T51 | Reference management (Zotero) — ongoing | M1 | W1-W4
T52 | Final proofread + reproducibility rerun from clean repo [GATE M4] | M5 | W4

## M3 Board
Member 3 — LiteCXR-Net Architecture Lead
YOUR HANDS-ON ML TASK: Designs & trains LiteCXR-Net + tuning (T20, T25)
TASKS YOU OWN (accountable)
ID | Epic | Task / Sub-issue | Week | M.stone | Depends on | Est. days | Deliverable
T17 | 3 LiteCXR | Design LiteCXR-Net (depthwise-separable blocks + compact head) | W2 | M1 | T10 | 2 | litecxrnet.py v1
T18 | 3 LiteCXR | Add width-multiplier alpha control (0.5 / 0.75 / 1.0) | W2 | M1 | T17 | 1 | Configurable width
T19 | 3 LiteCXR | Add lightweight channel-attention (SE-style) block | W2 | M1 | T17 | 1 | Attention block
T20 | 3 LiteCXR | [ML] Train LiteCXR-Net v1 from scratch | W2 | M1 | T18,T19,T13 | 2 | LiteCXR-Net checkpoint + curves
T21 | 3 LiteCXR | Baseline vs LiteCXR-Net comparison (accuracy / F1 / AUROC) | W2 | M1 | T20,T16 | 1 | Comparison table
T25 | 5 HP-Tune | [ML] LiteCXR-Net hyper-parameter tuning (alpha, LR, batch, weight decay) | W3 | M2 | T20 | 2 | Proposed-model tuning results
T46 | 12 Paper | Proposed Framework (LiteCXR-Net) section | W2-W4 | M4 | - | 2 | Paper sect. (method)
T50 | 12 Paper | Presentation slides | W4 | M4 | T41 | 2 | Slide deck
ALSO SUPPORTING (assist / review)
ID | Task / Sub-issue | Owner | Week
T01 | Create GitHub repo, branch strategy & folder layout (data/ src/ notebooks/ results/ paper/) | M1 | W1
T04 | Define shared config: image size (224 + 128 fast-mode), split ratios, metrics schema, checkpoint format | M5 | W1
T06 | Preprocessing module (resize, grayscale->3ch, normalise) | M2 | W1
T12 | Implement from-scratch baseline CNN (ResNet-18-style, NO pretrained weights) | M1 | W1
T14 | [ML] Train baseline CNN end-to-end to validate pipeline [GATE M0] | M1 | W1
T22 | [ML] Train LiteCXR-Net WITH the lung-focused shortcut-mitigation recipe | M2 | W2
T26 | [ML] Train & evaluate ablation: depthwise-separable vs standard convolution | M4 | W3
T27 | [ML] Train & evaluate ablation: with / without attention block | M4 | W3
T29 | [ML] Train & evaluate ablation: width-multiplier alpha sweep (0.5/0.75/1.0) | M4 | W3
T32 | Accuracy-efficiency trade-off (Pareto) curve | M4 | W3-W4
T35 | [ML] Train LiteCXR-Net control (NO recipe) for the robustness comparison | M5 | W3
T37 | Grad-CAM module (last convolutional layer) [GATE M3] | M5 | W3
T43 | Generate all figures (curves, Pareto, heatmaps, reliability) | M4 | W4
T47 | Experiments (efficiency + ablation) section | M4 | W4
T48 | Results + Discussion + Conclusion | M5 | W4
T51 | Reference management (Zotero) — ongoing | M1 | W1-W4
T52 | Final proofread + reproducibility rerun from clean repo [GATE M4] | M5 | W4

## M4 Board
Member 4 — Ablation-Model & Efficiency Lead
YOUR HANDS-ON ML TASK: Trains & evaluates all ablation model variants (T26-T29)
TASKS YOU OWN (accountable)
ID | Epic | Task / Sub-issue | Week | M.stone | Depends on | Est. days | Deliverable
T03 | 0 Setup | Compute setup: Colab/Kaggle GPU, requirements.txt, mixed-precision config | W1 | M0 | T01 | 1 | Reproducible environment
T26 | 6 Ablation | [ML] Train & evaluate ablation: depthwise-separable vs standard convolution | W3 | M2 | T20 | 1 | Ablation result A
T27 | 6 Ablation | [ML] Train & evaluate ablation: with / without attention block | W3 | M2 | T20 | 1 | Ablation result B
T28 | 6 Ablation | [ML] Train & evaluate ablation: with / without lung-focus recipe | W3 | M2 | T22 | 1 | Ablation result C
T29 | 6 Ablation | [ML] Train & evaluate ablation: width-multiplier alpha sweep (0.5/0.75/1.0) | W3 | M2 | T18 | 1 | Ablation result D
T30 | 7 Efficiency | Efficiency harness (params, FLOPs, latency CPU/GPU, memory, training time) [GATE M2] | W3 | M2 | T20 | 1 | efficiency.py
T31 | 7 Efficiency | Run computational analysis on baseline + LiteCXR-Net + alpha variants | W3 | M2 | T30,T16 | 1 | Efficiency table
T32 | 7 Efficiency | Accuracy-efficiency trade-off (Pareto) curve | W3-W4 | M2 | T31 | 1 | Pareto chart
T43 | 11 Analysis | Generate all figures (curves, Pareto, heatmaps, reliability) | W4 | M4 | T41 | 1 | Figure pack
T47 | 12 Paper | Experiments (efficiency + ablation) section | W4 | M4 | T41 | 2 | Paper sect. (experiments)
ALSO SUPPORTING (assist / review)
ID | Task / Sub-issue | Owner | Week
T01 | Create GitHub repo, branch strategy & folder layout (data/ src/ notebooks/ results/ paper/) | M1 | W1
T04 | Define shared config: image size (224 + 128 fast-mode), split ratios, metrics schema, checkpoint format | M5 | W1
T08 | Augmentation module (rotation, flip, jitter, CLAHE, random erasing) | M2 | W1
T14 | [ML] Train baseline CNN end-to-end to validate pipeline [GATE M0] | M1 | W1
T21 | Baseline vs LiteCXR-Net comparison (accuracy / F1 / AUROC) | M3 | W2
T25 | [ML] LiteCXR-Net hyper-parameter tuning (alpha, LR, batch, weight decay) | M3 | W3
T40 | [ML] Fit temperature-scaling calibration (learned scalar) + reliability, baseline vs proposed | M5 | W3-W4
T42 | Statistical comparison (significance, confidence intervals) | M5 | W4
T48 | Results + Discussion + Conclusion | M5 | W4
T50 | Presentation slides | M3 | W4
T51 | Reference management (Zotero) — ongoing | M1 | W1-W4
T52 | Final proofread + reproducibility rerun from clean repo [GATE M4] | M5 | W4

## M5 Board
Member 5 — Robustness, Calibration & Explainability Lead
YOUR HANDS-ON ML TASK: Trains the no-recipe control model + fits temperature-scaling calibration (T35, T40)
TASKS YOU OWN (accountable)
ID | Epic | Task / Sub-issue | Week | M.stone | Depends on | Est. days | Deliverable
T04 | 0 Setup | Define shared config: image size (224 + 128 fast-mode), split ratios, metrics schema, checkpoint format | W1 | M0 | T01 | 1 | config.yaml + metrics spec
T11 | 1 Data | Prepare external / source-stratified robustness set (test only) | W1-W2 | M1 | T06 | 2 | External test set ready
T13 | 2 Baseline | Shared training-loop template (from scratch) | W1 | M0 | T10 | 1 | train_template.py
T33 | 8 Robust | External-test protocol (label mapping, OOD metrics) | W3 | M3 | T11 | 1 | external_eval.py
T34 | 8 Robust | Baseline robustness test (internal vs external drop) | W3 | M3 | T33,T16 | 1 | Baseline OOD result
T35 | 8 Robust | [ML] Train LiteCXR-Net control (NO recipe) for the robustness comparison | W3 | M3 | T20 | 1 | Control model checkpoint
T36 | 8 Robust | LiteCXR-Net robustness test: recipe vs control (internal vs external drop) | W3 | M3 | T33,T22,T35 | 1 | Proposed OOD result
T37 | 9 XAI | Grad-CAM module (last convolutional layer) [GATE M3] | W3 | M3 | T20 | 1 | gradcam.py
T38 | 9 XAI | Lung-localisation faithfulness score (mask-overlap metric) | W3 | M3 | T37,T07 | 1 | faithfulness.py
T39 | 9 XAI | Faithfulness + heatmaps: baseline vs LiteCXR-Net | W3 | M3 | T38,T16 | 1 | XAI figures + scores
T40 | 10 Calib | [ML] Fit temperature-scaling calibration (learned scalar) + reliability, baseline vs proposed | W3-W4 | M3 | T16,T20 | 1 | Calibration result
T41 | 11 Analysis | Consolidate all metrics into master results tables | W4 | M4 | T31,T36,T39 | 1 | Master results tables
T42 | 11 Analysis | Statistical comparison (significance, confidence intervals) | W4 | M4 | T41 | 1 | Stats appendix
T48 | 12 Paper | Results + Discussion + Conclusion | W4 | M4 | T41 | 2 | Paper sect. (results)
T52 | 12 Paper | Final proofread + reproducibility rerun from clean repo [GATE M4] | W4 | M4 | T47,T48 | 1 | Camera-ready + repro log
ALSO SUPPORTING (assist / review)
ID | Task / Sub-issue | Owner | Week
T01 | Create GitHub repo, branch strategy & folder layout (data/ src/ notebooks/ results/ paper/) | M1 | W1
T02 | Set up experiment tracking (W&B/TensorBoard) + fixed-seed reproducibility standard | M1 | W1
T07 | [ML] Train a lightweight lung-segmentation U-Net to generate lung masks | M2 | W1-W2
T09 | Stratified 70/15/15 split (fixed seed) + saved index files | M2 | W1
T14 | [ML] Train baseline CNN end-to-end to validate pipeline [GATE M0] | M1 | W1
T20 | [ML] Train LiteCXR-Net v1 from scratch | M3 | W2
T23 | Tune augmentation / recipe strength for robustness | M2 | W3
T30 | Efficiency harness (params, FLOPs, latency CPU/GPU, memory, training time) [GATE M2] | M4 | W3
T31 | Run computational analysis on baseline + LiteCXR-Net + alpha variants | M4 | W3
T44 | Introduction + Related Work | M1 | W1-W4
T46 | Proposed Framework (LiteCXR-Net) section | M3 | W2-W4
T47 | Experiments (efficiency + ablation) section | M4 | W4
T49 | Abstract | M1 | W4
T50 | Presentation slides | M3 | W4
T51 | Reference management (Zotero) — ongoing | M1 | W1-W4

## Dashboard
STATUS DASHBOARD (auto from Master Task List)
Total tasks | 52
Not started | 52
In progress | 0
Blocked | 0
Done | 0
% Complete | 0%
Owned tasks per member (incl. [ML] count)
Member | Owned tasks | ML tasks | Done
M1 | 9 | 2 | 0
M2 | 10 | 3 | 0
M3 | 8 | 2 | 0
M4 | 10 | 4 | 0
M5 | 15 | 2 | 0